## Gantt
车牌自动识别算法的设计与实现 |  |  | project manager：胡亿豪、洪彬
Input column | [5 empty] | Project start date: | [5 empty] | 2021-12-26 |  |  |  | 1
Calculated column
[6 empty] | WEEK 53 |  |  |  |  | WEEK 1
[6 empty] | 2021-12-27 | 2021-12-28 | 2021-12-29 | 2021-12-30 | 2021-12-31 | 2022-01-01 | 2022-01-02 | 2022-01-03 | 2022-01-04 | 2022-01-05
TASK NAME | START DATE | WORK DAYS | END DATE | TEAM MEMBER | % | M | T | W | T | F | S | S | M | T | W
Phase 1:实现车牌识别，颜色识别，文本提取 | 2021-12-26 | 6 | 2021-12-31 |  | 50%
Task 01：实现车牌识别1 | 2021-12-26 | 1 | 2021-12-26 | 胡亿豪 | 20% | bar: 2021-12-27 to 2021-12-28
Subtask 1：实现车牌的初始化处理 | 2021-12-26 | 0.5 | 2021-12-24 | 胡亿豪 | 10% | bar: 2021-12-27
Subtask 2：实现车牌外轮廓读取 | 2021-12-27 | 1 | 2021-12-27 | 胡亿豪 | 10% | bar: 2021-12-28
Task 02：实现车牌识别2：实现矩形矫正 | 2021-12-28 | 1 | 2021-12-28 | 胡亿豪 | 10% | bar: 2021-12-29
Task 03：实现车牌识别3：实现颜色判断 | 2021-12-29 | 1 | 2021-12-29 | 胡亿豪 | 10% | bar: 2021-12-30
Task 04：实现匹配字符 | 2021-12-30 | 1 | 2021-12-30 | 胡亿豪 | 5% | bar: 2021-12-31
Task 05：提取字符功能 | 2021-12-31 | 1 | 2021-12-31 | 胡亿豪 | 5% | bar: 2022-01-01
Phase 2 ：软件界面设计 | 2022-01-01 | 5 | 2022-01-06 |  | 40% | bar: 2022-01-02
Task 06：chuli.py 界面设计 | 2022-01-01 | 1 | 2022-01-01 | 洪彬 | 5% | bar: 2022-01-02
Task 07：main.py 页面设计 | 2022-01-01 | 1 | 2022-01-01 | 洪彬 | 10% | bar: 2022-01-03
Task 08：测试软件实现功能 | 2022-01-02 | 1 | 2022-01-02 | 洪彬 | 10% | bar: 2022-01-03 to 2022-01-04
Task 09：编写实验文档 | 2022-01-03 | 1 | 2022-01-03 | 洪彬 | 10%
Task 10：编写实验文档 | 2022-01-04 | 1 | 2022-01-04 | 胡亿豪，洪彬 | 5% | bar: 2022-01-05

## Readme
Getting started guide
| • | Enter the [Project Name], [Project Manager], and [Company Name].
| • | Enter the Project Start Date (P3). This will automatically update the dates shown in the timeline.
| • | Add details of your tasks, such as TYPE, TASK NAME, START DATE, the number of WORKDAYS, and TEAM MEMBER.
|  |  | Note: | Type can be Phase (P), Task (T), or Subtask (S).
| • | To change the range of dates displayed in the timeline area, just slide the scroll bar.
|  |  | Note: | Do not change the dates in the timeline manually.
| • | To add more tasks:
|  |  | Step 1: | Copy a single row or several rows at once.
|  |  | Step 2: | Select the row after the last task (Row 36), then right-click and select Paste or Insert Copied Cells (recommended).
Note: If you want to insert the copied cells between tasks, just select any task's row, then right-click and select Insert Copied Cells.
| • | To add more dates in the timeline:
|  |  | Step 1: | Copy one-week columns (e.g. AW-BA)
|  |  | Step 2: | Select the column after the last date (BB), then right-click and select Insert Copied Cells.
The calculation for END DATE
| • | If you enter a start date, by default, the end date is the same as the start date.
| • | Once you add the number of workdays, the end date is automatically updated. Weekends are not included in the calculation.
|  |  | Note: | Do not enter end dates manually since the END DATE is a calculated column.
The calculation for Phases
| • | You can enter the start date and number of workdays of a Phase manually.
| • | However, if you want to do calculation automatically based on its tasks, use the following formulas:
|  |  | START DATE |  | =MIN(range_of_its_tasks_start_dates)
|  |  | WORK DAYS |  | =IF(ISBLANK(phase_start_date),"",NETWORKDAYS(phase_start_date,MAX(range_of_its_tasks_end_dates)))
The calculation for Tasks
| • | You can can enter the start date, number of workdays, and % completion of a tasks manually.
| • | However, if you want to do calculation automatically based on its subtasks, use the following formulas:
|  |  | START DATE |  | =MIN(range_of_its_subtasks_start_dates)
|  |  | WORKDAYS |  | =IF(ISBLANK(task_start_date),"",NETWORKDAYS(task_start_date,MAX(range_of_its_subtasks_end_dates)))
|  |  | % |  | =SUMPRODUCT(range_of_its_subtasks_workdays,range_of_its_subtasks_%completed/SUM(range_of_its_subtasks_workdays)